JONIK NDOVU FARM

90-Day Capital-Raising Plan

VERSION 3.0  |  INVESTOR WORKING DRAFT  |  OCTOBER 2026

Objective: build a credible investor pipeline and move from concept materials to qualified discussions and a diligence-ready opportunity. The schedule assumes the project team can respond promptly and commission priority professional work.

## Days 1–15 | Lock the facts

Approve the 12–15-unit range and US$2.4m all-in capital target; obtain written land terms; appoint project lead; build document register; confirm ownership/title evidence; commission survey and QS scope; agree confidentiality process.

## Days 16–30 | Build investor-grade evidence

Complete sources & uses with QS input; prepare base/downside financial model; compile location/access/utility evidence; map planning and environmental approvals; benchmark competitors and rate positioning; document operator options.

## Days 31–45 | Segment and qualify prospects

Create a researched list of hospitality investors, family offices, Kenyan/East African business groups, impact-aligned investors and strategic operators. Score fit, ticket size, geography, hospitality experience and decision access. Do not represent names as interested without evidence.

## Days 46–60 | Controlled outreach

Send personalized teaser to qualified prospects; ask for a 20–30 minute introductory call; track contact, response, next step and source. Share the full deck only where appropriate; share sensitive documents only under NDA and with permission.

## Days 61–75 | Meetings and diligence

Use one consistent pitch; log objections; provide a controlled data room; answer questions with evidence; arrange site visit where useful; maintain an issues log and weekly investor pipeline review.

## Days 76–90 | Structure and advance

Identify potential lead investor(s); compare indicative structures; align governance and decision rights; seek non-binding expressions of interest where appropriate; instruct legal/tax advisers before term sheets or binding commitments.

# Weekly dashboard

Number of researched prospects and verified decision-makers.

Personalized outreaches sent, responses, introductory calls and follow-up meetings.

Investors progressing to NDA/data room/site visit.

Top five objections and evidence needed to address each.

Readiness blockers: land, QS cost plan, market study, permits, operator and model.

Cash required to complete diligence and keep the project moving.

# Investor segments to prioritize

Lead equity investor with hospitality or real-asset experience.

Kenyan/East African family offices and business owners with long-term investment horizon.

Boutique hotel/lodge operators or management partners seeking a distinctive asset.

Impact-aligned tourism investors, where measurable environmental/community outcomes can be supported.

Co-investors who can follow a credible lead rather than create a fragmented decision process.

# Outreach rule

Never bulk-send an identical message to a large unqualified list. Use a short personalized note, a clear ask, and a transparent statement that the opportunity is at concept stage and figures are subject to diligence.